## Vendor Profile
Vendor Name | Service Provided | Data Accessed | Integration Type | Criticality | Regulatory Impact | Contract Owner
CloudPay Services | Payment processing and settlement | Transaction data, limited customer PII | API-based integration | High | PCI-DSS, GDPR | Procurement / Legal

## Vendor Due Diligence
Control Area | Due Diligence Question | Evidence Required | Risk Level | Status
Information Security | Is the vendor certified to ISO 27001 or equivalent security standard? | ISO 27001 certificate or independent audit report | High | Pending
Data Protection | Does the vendor comply with GDPR requirements for data processing? | Data processing agreement (DPA), privacy policy | High | Pending
Regulatory Compliance | Is the vendor compliant with PCI-DSS requirements? | PCI-DSS attestation of compliance (AOC) | High | Pending
Business Continuity | Does the vendor have documented and tested BCP/DR plans? | BCP/DR documentation and test reports | Medium | Pending
Incident Response | Does the vendor have an incident response and breach notification process? | Incident response policy and notification SLAs | Medium | Pending

## Vendor Risk Register
Risk ID | Vendor | Risk Description | Threat | Vulnerability | Likelihood (1–5) | Impact (1–5) | Risk Score | Existing Controls | Risk Treatment | Residual Risk | Risk Owner
VR-01 | CloudPay Services | Vendor data breach exposing transaction data | External cyber attack on vendor systems | Weak security controls at vendor | 3 | 5 | 15 | Vendor security questionnaire, SLA clauses | Mitigate | Medium | Vendor Management
VR-02 | CloudPay Services | Vendor service outage impacting payment processing | Infrastructure failure at vendor | Single vendor dependency with limited failover | 3 | 4 | 12 | SLA uptime commitments, incident response procedures | Mitigate | Medium | Operations Team
VR-03 | CloudPay Services | Vendor non-compliance with PCI-DSS requirements | Compliance failure or audit finding | Insufficient ongoing compliance monitoring | 2 | 5 | 10 | Contractual compliance clauses, periodic vendor reviews | Mitigate | Medium | Compliance Team